## groupe
ETU003082 | ANDRIAMANANTENA Falisoa Haris Ryan
ETU003224 | RAZANAKOTO Miharisoa Hasimanitriniaina

## to_do
Catégorie | Module | Pages | Taches | Type | Qui | Estimation | Temps passé | Reste à faire | Avancement
Shared | Conception |  | MCD looping | Base | ETU003224 | 10 | 10 | 0 | 100%
Shared | Initialisation |  | Initialisation du projet + Docker + init commit sur GITHUB | Init | ETU003082 | 15 | 15 | 0 | 100%
Shared | Initialisation |  | Creation des models suivant le MCD (constructors + getters + setters) | Init | ETU003082 | 15 | 15 | 0 | 100%
Backoffice | Article management | article-add | Form Create (Use TinyMCE) | Affichage | ETU003082 | 15 | 10 | 0 | 100%
Backoffice | Article management | article-edit | Form Edit (Use TinyMCE again) | Affichage | ETU003082 | 10 | 15 | 0 | 100%
Backoffice | Article management | article-list-admin | List Article | Affichage | ETU003224 | 15 | 15 | 0 | 100% | Col | Currently Working on
Backoffice | Article management | article-detail | Consult article | Affichage | ETU003224 | 10 | 10 | 0 | 100% |  | for 3082
Backoffice | Article management | article-list-admin | Button Edit and Delete Article | Affichage | ETU003224 | 2 | 3 | 0 | 100% |  | for 3224
Backoffice | Article management | article-add & edit | Save: Generate Slug title | Metier | ETU003082 | 10 | 7 | 0 | 100%
Backoffice | Article management | article-add & edit | Save condition: if created_at is null then use date.now(), else do nothing to avoid erasing OG date | Metier | ETU003082 | 5 | 17 | 0 | 100%
Backoffice | Article management | article-edit | Edit, Delete | Metier | ETU003082 | 5 | 5 | 0 | 100%
Backoffice | Article management | article-list | Get All | Metier | ETU003224 | 17 | 15 | 0 | 100%
Backoffice | Article management | Article | Integration CUD | Integration | ETU003082 | 40 | 40 | 0 | 100%
Shared | Article management | Article | Integration R | Integration | ETU003224 | 20 | 20 | 0 | 100%
Shared | User Management | login-form | Form login, mainly for Admin rn + "Visit as guest" option link to access F.O without credentials | Affichage | ETU003082 | 10 | 10 | 0 | 100%
Shared | User Management | login-form | "Visit as guest" | Metier | ETU003224 | 5 | 5 | 0 | 100%
Shared | User Management | login-form | Check login credentials | Metier | ETU003082 | 10 | 10 | 0 | 100%
Shared | User Management | login-form | Redirect to article-list (guest or other) or redirect to article-list-admin (admin) | Metier | ETU003224 | 3 | 2 | 0 | 100%
Shared | User Management | login-form | Integration Login | Integration | ETU003224 | 10 | 10 | 0 | 100%
Frontoffice | Article management | article-list | Copy Paste page from the backoffice but remove the edit, add, delete | Affichage | ETU003224 | 5 | 3 | 0 | 100%
Frontoffice | Article management | article-detail | Reuse the same page as the one in backoffice | Affichage | ETU003224 | 5 | 3 | 0 | 100%
Frontoffice | Article management | article-list | Get All: Reuse same func established in the B.O | Metier | ETU003224 | 5 | 2 | 0 | 100%
Frontoffice | Article management | article-detail | Get Specific Article | Metier | ETU003224 | 10 | 10 | 0 | 100%
Frontoffice | Article management | article-detail | Get Spe.Arti: Rewrite URL using < ID-Created_At-Slug>.html format | Metier | ETU003224 | 10 | 10 | 0 | 100%
Frontoffice | Article management | article-detail | Get Spe.Arti: Set the content of the "article-detail" page to the Article.content | Integration | ETU003224 | 10 | 10 | 0 | 100%
Backoffice | Article management | article-add & edit | uploadImage: Instead of putting the image binary inside the article.content, use an upload to min the char stored in db | Metier | ETU003082 | 20 | 20 | 0 | 100%
Backoffice | Article management | article-add & edit | uploadImage: optimization of image size + jpg compression (changed to webp in the end) | Metier | ETU003082 | 15 | 15 | 0 | 100%
Backoffice | Refactorisation |  | Refactor all the previous Java Spring Boot -> Php Vanilla w/ AI help | Affichage | ETU003082 | 20 | 20 | 0 | 100%
Backoffice | Refactorisation |  | Refactor all the previous Java Spring Boot -> Php Vanilla w/ AI help | Metier | ETU003082 | 25 | 25 | 0 | 100%
Backoffice | Refactorisation |  | Refactor all the previous Java Spring Boot -> Php Vanilla w/ AI help | Integration | ETU003082 | 35 | 35 | 0 | 100%
Shared | Optimisation |  | compression gzip | Metier | ETU003224 | 5 | 5 | 0 | 100%
Shared | Optimisation |  | ajout de balise meta | Metier | ETU003224 | 5 | 5 | 0 | 100%
Shared | Optimisation |  | cdn to local font + js | Metier | ETU003082 | 5 | 5 | 0 | 100%
Shared | Optimisation |  | minify css | Metier | ETU003082 | 5 | 5 | 0 | 100%
Shared | Optimisation |  | caching js and css | Metier | ETU003082 | 5 | 5 | 0 | 100%
Backoffice | Fix | article-list-admin | fix list redirection if connected as admin (only show the list for the admin, not the guest's) | Metier | ETU003224 | 5 | 3 | 0 | 100%
Shared | Conception |  | adding cover image upload | Base | ETU003224 | 5 | 3 | 0 | 100%
Shared | Article management | article-add | adding cover image upload form | Affichage | ETU003224 | 5 | 5 | 0 | 100%
Shared | Article management | article-add | handle cover image upload: reuse the imageUpload function, just modify the path to uploads/cover | Metier | ETU003224 | 5 | 5 | 0 | 100%
Shared | Article management | article-add | adding cover image upload | Integration | ETU003224 | 10 | 10 | 0 | 100%
Shared | Document Technique |  | adding cover image upload | Integration | ETU003224 | 30 | 30 | 0 | 100%

## detail_avancement
Ligne | Total | 2026-03-29 | 2026-03-30 | 2026-03-31
2 | 10 | 10
3 | 15 | 15
4 | 15 | 15
5 | 10 | 10
6 | 15 |  | 15
7 | 15 |  | 15
8 | 10 |  | 10
9 | 3 |  | 3
10 | 7 | 7
11 | 17 | 2 | 15
12 | 5 | 5
13 | 0
14 | 40 | 20 | 20
15 | 20 |  | 20
16 | 10 |  | 10
17 | 5 |  | 5
18 | 10 |  | 10
19 | 2 |  | 2
20 | 10 |  | 10
22 | 3 |  |  | 3
23 | 3 |  |  | 3
24 | 2 |  |  | 2
25 | 10 |  |  | 10
26 | 10 |  |  | 10
27 | 10 |  |  | 10
29 | 20 |  | 20
30 | 15 |  | 15
32 | 20 |  | 20
33 | 25 |  | 25
34 | 35 |  | 35
36 | 5 |  |  | 5
37 | 5 |  |  | 5
38 | 5 |  |  | 5
39 | 5 |  |  | 5
40 | 5 |  |  | 5
42 | 3 |  |  | 3
44 | 3 |  |  | 3
45 | 5 |  |  | 5
46 | 5 |  |  | 5
47 | 10 |  |  | 10
49 | 30 |  |  | 30